## Sheet1
WIP
Target Date | 2022-03-01
Valkyrie still to do | Phase 1 Beta | RC Phase 1 | Phase 2 Beta | RC Phase 2 | To investigate | To Design | To Prototype | Notes
Enclosure
Drawer for Flament temperature ?C | x
Chris -o- sol Spool holder | x | [5 empty] | C
dibond enclosure | x
Fan Air cooled part cooling | x
Heater for chamber |  |  | x |  | ??? |  |  | Forced air, silicone
heater for Dry box | x |  |  |  |  | C | C
Fully enclosed 80C |  |  | x
Carbon Filter |  |  | x
Calcium Silicate liner for chamber and dry box |  |  | x
Clear front door and Seal | TBD |  | x |  |  |  |  | Need some thourghts and ideas
Seal Gear box to floor |  |  | x |  | R
Top/Lid and seal chamber | TBD |  | x |  |  |  |  | Need some thourghts and ideas
Top/Lid and seal Dry box | TBD |  | x |  |  |  |  | Need some thourghts and ideas
Tool Head
Types of tool head | TBD |  | TBD |  |  |  |  | Which type do we prototype for?
water cooled extruder |  |  | TBD |  | RCM
Z probe , IR ,Inductive ,BL touch, Or Custom | TBD |  |  |  | RCM |  |  | Chris option pick as required.
Cable management to Tool head | TBD |  | TBD |  | ?? |  |  | Need some thourghts and ideas
PCB for x caridge | TBD |  | TBD |  |  |  |  | Need some thourghts and ideas
filament path from Draw to tool head | TBD |  | TBD |  | ?? |  |  | Need some thourghts and ideas
Kinematics
All metal parts in the heated chamber |  |  | x
Filament Run out sensor | TBD |  | TBD |  |  |  |  | Notification via sounder and o text? Value for effort is it needed
Safety Features over temperature and earthiing | x |  | TBD |  |  |  |  | Cut power to SSR, AND chamberand dry box heater, try to keep fans runnng, Audioble warning, text message
Hard buttons, E-Stop, Filament change etc | TBD |  | TBD |  |  |  |  | Is it needed? Or a nice to have ?
Display Screen | TBD |  | TBD
Sample Test print pre build calibration check | x |  |  |  |  | M |  | to add bearing hole
magnectic PEI sheet | TBD |  | TBD |  |  |  |  | To discuse